## 0. Guidance & Instructions
MANUAL TESTING DOCUMENTATION GUIDE
1. TEST PLAN
Purpose: Defines overall testing approach, scope, timeline, and resources.
Key Components: Project info, scope, testing types, environment, timeline, resources, risks, assumptions.
Who fills it: QA Lead/Test Manager
When: Before testing begins
2. TEST SCENARIOS
Purpose: Describes high-level business situations/workflows to be tested.
Key Components: Scenario ID, name, description, pre-conditions.
Who fills it: QA Lead/Business Analyst
When: During test planning phase
Example: "User Login Scenario" - User provides credentials and system validates them
3. TEST CASES
Purpose: Detailed step-by-step instructions for testing specific functionality.
Key Components: Test case ID, scenario ID, title, pre-conditions, steps, expected result, priority.
Who fills it: QA Engineer/SDET
When: During test design phase
Best Practice: Each test case should be independent and reusable
4. TEST DATA
Purpose: Documents all test data needed for test execution.
Key Components: Data ID, type, test data values, purpose/usage.
Who fills it: QA Engineer/Test Data Manager
When: Before test execution
Important: Use realistic but safe data; never use real production data
5. TEST EXECUTION DOCUMENT
Purpose: Records actual execution results of test cases.
Key Components: Test case ID, cycle, title, executed by, execution date, pass/fail status, defect ID.
Who fills it: QA Engineer
When: During test execution
Status Options: Pass (expected behavior matches actual), Fail (discrepancy found), Not Executed (skipped)
6. TRACEABILITY MATRIX
Purpose: Maps requirements to test cases to ensure complete coverage.
Key Components: Requirement ID, test case ID, requirement description, coverage status.
Who fills it: QA Lead
When: Throughout testing lifecycle
Benefit: Identifies gaps; ensures all requirements are tested
7. DEFECT REPORT
Purpose: Documents all defects/bugs found during testing.
Key Components: Defect ID, test case ID, title, description, severity, priority, status, assigned to.
Who fills it: QA Engineer
When: When defect is discovered
Severity: Critical (blocks functionality), High (major issue), Medium (moderate impact), Low (minor issue)
Priority: Should be set based on business impact
8. TEST SUMMARY REPORT
Purpose: High-level overview of testing results and recommendations.
Key Components: Execution summary, defect summary, metrics, conclusion, recommendation.
Who fills it: QA Lead/Test Manager
When: At end of test cycle
Audience: Stakeholders, Project Manager, Development Lead
KEY METRICS
Pass Rate = (Test Cases Passed / Test Cases Executed) × 100%
Requirement Coverage = (Requirements Tested / Total Requirements) × 100%
Defect Density = Total Defects / Total Test Cases
Escape Rate = Defects found in production / Total defects found (in testing + production)

## 1. Test Plan
TEST PLAN
Project Info
Project Name: | Notes Application
Date: | 06-05-2026
Prepared By: | Nikitha Adupala
SCOPE | Purpose
Features to be Tested: | Validate UI & API, and UI–API synchronization manually
Scope
UI login, note creation, API validations, E2E sync, negative scenarios
TESTING TYPE
Functional Testing | Test Strategy
Regression Testing | UI Testing, API Testing using Postman, E2E Validation
Automation Tools | Tools
Selenium, Pytest, Postman, Requests Library
TEST ENVIRONMENT
Environment
Browser/OS: | Windows 11, Chrome Browser, Python
TIMELINE
Start Date: | 2026-05-05
End Date: | 2026-05-07
RESOURCES
QA Lead: | Nikitha Adupala
QA Resources: | QA Engineers, Automation Test Engineers, API Testers
RISKS & ASSUMPTIONS
Risks: | Application downtime during testing
API server unavailability
Test data inconsistency
Assumptions: | Test environment is stable and accessible
Valid user credentials are available
Notes application UI And API remain unchnaged during testing

## 2. Test Scenarios
Scenario ID | Scenario Name | Description | Pre-Condition
TS-01 | UI Login Validation | Validate successful UI login functionality | User account should exist
TS-02 | Create Note via UI | Validate note creation through UI | User logged in
TS-03 | Note should appear instantly in UI list | Validate note appears instantly without refresh | Note created
TS-04 | API GET /notes returns list | Validate GET /notes API response | Valid API token
TS-05 | UI-created note must appear in API | Validate UI-created note matches API | Note created via UI
TS-06 | Delete Note via API | Validate note deletion via API | Note exists
TS-07 | Deleted note must disappear from UI | Validate deleted note disappears from UI | Note deleted via API
TS-08 | Negative Validation | Validate invalid inputs and API errors | Application available

## 3. Test Cases
Test Case ID | Scenario ID | Test Case Title | Pre-conditions | Steps | Expected Result | Priority | Status
TC-UI-01 | TS-01 | Verify successful UI login | Valid credentials available | 1. Open Website | Dashboard displayed successfully | High | Not Executed
2. Enter credentials
3. Click login
TC-UI-02 | TS-02 | Verify create note via UI | User logged in | 1. Click Add Note | Note should be created successfully | High | Not Executed
2. Enter title & description
3. Click Save
TC-UI-03 | TS-03 | Verify note appears instantly in UI | Note created successfully | 1. Create note | Newly created note should appear instantly | High | Not Executed
2. Observe notes list without refresh
TC-API-01 | TS-04 | Validate GET /notes API | API token available | 1. Call GET/notes API | Status code 200 with notes list | High | Not Executed
2. Validate response
TC-E2E-01 | TS-05 | Verify UI- created note apprears in API | Note created via UI | 1. Capture UI note data | UI and API data should match | Critical | Not Executed
2. Call GET API
3. Compare values
TC-API-02 | TS-06 | Verify delete note via API | Existing note ID available | 1. Send DELETE request | Note should delete successfully | High | Not Executed
2. Validate response
TC-E2E-02 | TS-07 | Verify API deleted note disappears from UI | Note deleted via API | 1. Refresh UI | Deleted note should disappear from UI | Critical | Not Executed
2. Check notes list
TC-API-03 | TS-08 | Verify API response time | API available | 1. Call GET /notes API | Response time should be below 2 seconds | High | Not Executed
2. Measure response time
TC-NEG-01 | TS-09 | Verify negative scenarios (UI & API) | Application and API available | 1. Enter invalid login data | Proper validation and error messages should display | High | Not Executed
2. Submit blank note
3. Send API request without token

## 4. Test Data
Data ID | Data Type | Test Data | Usage/Purpose
TD-01 | Valid Login Credentials | EMAIL: user@example.com | Used for successful UI/API login validation
PASSWORD: Password@123
TD-02 | Invalid Login Credentials | EMAIL: invalid@example.com | Used for negative login validation
PASSWORD: wrongpass
TD-03 | Valid Note Data | Title: QA Note | Used for create note functionality
Description: Testing Notes App
TD-04 | API Token | Authentication token | Used for authorized API requests
TD-05 | Payment Data | Card: 4532015112830366, CVV: 123 | Payment processing (test card)
TD-06 | Address Data | City: Hyderabad, Country: INDIA, Zip: 10001 | Address validation
TD-07 | Note ID | Existing note ID from API response | Used for update/delete note testing
TD-08 | Invalid Note ID | Random invalid ID | Used for negative delete API testing
TD-09 | Empty Note Data | Title: "" Description: "" | Used for blank field validation

## 5. Test Execution
Test Case ID | Cycle | Title | Status
TC-UI-01 | Cycle-1 | Verify successful UI login | Pass
TC-UI-02 | Cycle-1 | Verify create note via UI | Pass
TC-UI-03 | Cycle-1 | Verify note appears instantly in UI | Pass
TC-API-01 | Cycle-1 | Validate GET /notes API | Pass
TC-E2E-01 | Cycle-1 | Verify UI-created note appears in API | Pass
TC-API-02 | Cycle-1 | Verify delete note via API | Pass
TC-E2E-02 | Cycle-1 | Verify API deleted note disappears from UI | Pass
TC-API-03 | Cycle-1 | Verify API response time | Pass
TC-NEG-01 | Cycle-1 | Verify negative scenarios (UI & API) | Pass

## 6. Traceability Matrix
Requirement ID | Test Case ID | Requirement Description | Coverage Status
FR-01 | TC-UI-01 | UI login should work | Covered
FR-02 | TC-UI-02 | Create note via UI | Covered
FR-03 | TC-UI-03 | Note should appear instantly in UI list | Covered
FR-04 | TC-API-01 | API GET /notes returns list | Covered
FR-05 | TC-E2E-01 | UI-created note must appear in API | Covered
FR-06 | TC-API-02 | Delete note via API | Covered
FR-07 | TC-E2E-02 | Deleted note must disappear from UI | Covered
FR-08 | TC-API-03 | API response < 2s | Covered
FR-09 | TC-NEG-01 | Negative scenarios (UI & API) | Covered

## 7. Defect Report
Defect ID | Test Case ID | Title | Description | Severity | Priority | Status | Assigned To
BUG-001 | TC-NEG-01 | Invalid login error message mismatch | Application displays incorrect validation message for invalid login attempt | Medium | High | Open | Developer Team
BUG-002 | TC-UI-03 | Note not appearing instantly in UI | Newly created note requires manual refresh to appear in notes list | High | Critical | Open | Frontend Team
BUG-003 | TC-API-03 | API response time exceeds 2 seconds | GET /notes API response time observed above expected threshold | Medium | Medium | In Progress | Backend Team
BUG-004 | TC-E2E-01 | UI and API note data mismatch | Created note title in UI does not match API response data | High | High | Open | Backend Team
BUG-005 | TC-API-02 | Delete API returns incorrect status code | DELETE /notes API returns 500 instead of 200 | Critical | Critical | Open | API Team

## 8. Test Summary Report
TEST SUMMARY REPORT
PROJECT INFORMATION
Project Name: | Notes Application – UI + API Hybrid Testing
Test Cycle: | Cycle-1
Prepared By: | Nikitha Adupala
EXECUTION SUMMARY
Total Test Cases: | 15
Test Cases Executed: | 15
Test Cases Passed: | Total 15 passed
Test Cases Failed: | 0
DEFECT SUMMARY
Total Defects: | 5
Critical Defects: | 2
High Defects: | 2
Medium Defects: | 1
Low Defects: | 0
CONCLUSION
Testing Status: | In Progress
Overall Recommendation: | Not Ready for Production